## T_E
Execution ID | Test Case ID | Module | Submodule | Test Type | Test Scenario | Test Data | Expected Result | Actual Result | Status | Defect ID | Remarks
EXEC-001 | TC-FIN-001 | Finance | General Ledger | Functional | Record financial transaction | GL-1001 | Transaction should be saved successfully | Transaction was saved successfully | Pass | - | Verified
EXEC-002 | TC-FIN-002 | Finance | General Ledger | UI | Verify transaction entry fields | Income ₹10000 | All fields should be displayed correctly | All fields displayed correctly | Pass | - | Verified
EXEC-003 | TC-FIN-003 | Finance | General Ledger | Regression | Verify existing ledger transaction | GL-1002 | Existing transaction should remain available | Existing transaction displayed correctly | Pass | - | Regression passed
EXEC-004 | TC-FIN-004 | Finance | General Ledger | Integration | Verify ledger posting | GL-1003 | Transaction should reflect in financial records | Transaction reflected correctly | Pass | - | Integration verified
EXEC-005 | TC-FIN-005 | Finance | General Ledger | Object | Verify ledger window objects | Save button | Save button should be available | Save button displayed correctly | Pass | - | Object verified
EXEC-006 | TC-FIN-006 | Finance | Accounts Payable | Functional | Process supplier payment | VEN-001 ₹20000 | Payment should be processed successfully | Payment processed successfully | Pass | - | Verified
EXEC-007 | TC-FIN-007 | Finance | Accounts Payable | UI | Verify payment screen | Payment details | Payment fields should be displayed correctly | Payment fields displayed correctly | Pass | - | Verified
EXEC-008 | TC-FIN-008 | Finance | Accounts Payable | Regression | Verify previous payment records | PAY-1001 | Previous records should remain accessible | Previous records accessible | Pass | - | Regression passed
EXEC-009 | TC-FIN-009 | Finance | Accounts Payable | Integration | Verify payment updates payable balance | VEN-001 | Payable balance should be updated | Payable balance updated correctly | Pass | - | Integration verified
EXEC-010 | TC-FIN-010 | Finance | Accounts Payable | Object | Verify payment button | Process Payment | Button should be enabled | Button enabled correctly | Pass | - | Object verified
EXEC-011 | TC-FIN-011 | Finance | Accounts Receivable | Functional | Record customer payment | CUST-001 ₹15000 | Payment should be recorded | Payment recorded successfully | Pass | - | Verified
EXEC-012 | TC-FIN-012 | Finance | Accounts Receivable | UI | Verify customer payment fields | CUST-001 | Required fields should be visible | Required fields displayed | Pass | - | Verified
EXEC-013 | TC-FIN-013 | Finance | Accounts Receivable | Regression | Verify outstanding amount | INV-1001 | Outstanding amount should remain accurate | Outstanding amount displayed correctly | Pass | - | Regression passed
EXEC-014 | TC-FIN-014 | Finance | Accounts Receivable | Integration | Verify invoice updates receivable | INV-1002 | Receivable should be created | Receivable created correctly | Pass | - | Integration verified
EXEC-015 | TC-FIN-015 | Finance | Accounts Receivable | Object | Verify payment control | Submit Payment | Control should be available | Control displayed correctly | Pass | - | Object verified
EXEC-016 | TC-FIN-016 | Finance | Fixed Assets | Functional | Add company asset | FA-1001 ₹100000 | Asset should be created | Asset created successfully | Pass | - | Verified
EXEC-017 | TC-FIN-017 | Finance | Fixed Assets | UI | Verify asset fields | Machine asset | Asset fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-018 | TC-FIN-018 | Finance | Fixed Assets | Regression | Verify asset history | FA-1001 | Asset history should remain available | Asset history displayed | Pass | - | Regression passed
EXEC-019 | TC-FIN-019 | Finance | Fixed Assets | Integration | Verify depreciation update | FA-1001 | Depreciation should reflect in records | Depreciation reflected correctly | Pass | - | Integration verified
EXEC-020 | TC-FIN-020 | Finance | Fixed Assets | Object | Verify depreciation control | Calculate Depreciation | Control should be available | Control displayed correctly | Pass | - | Object verified
EXEC-021 | TC-SAL-001 | Sales | Customer Management | Functional | Create customer | CUST-001 ABC Technologies | Customer should be created | Customer created successfully | Pass | - | Verified
EXEC-022 | TC-SAL-002 | Sales | Customer Management | UI | Verify customer form | Customer details | Form fields should display correctly | Form displayed correctly | Pass | - | Verified
EXEC-023 | TC-SAL-003 | Sales | Customer Management | Regression | Verify existing customer | CUST-002 | Existing customer should remain available | Customer displayed correctly | Pass | - | Regression passed
EXEC-024 | TC-SAL-004 | Sales | Customer Management | Object | Verify customer save button | Save Customer | Button should work correctly | Button worked correctly | Pass | - | Object verified
EXEC-025 | TC-SAL-005 | Sales | Customer Management | Functional | Update customer | CUST-003 Phone Number | Customer details should update | Details updated successfully | Pass | - | Verified
EXEC-026 | TC-SAL-006 | Sales | Quotation Management | Functional | Create quotation | QT-1001 ₹30000 | Quotation should be created | Quotation created successfully | Pass | - | Verified
EXEC-027 | TC-SAL-007 | Sales | Quotation Management | UI | Verify quotation fields | Product and discount | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-028 | TC-SAL-008 | Sales | Quotation Management | Regression | Verify existing quotation | QT-1002 | Quotation should remain accessible | Quotation accessible | Pass | - | Regression passed
EXEC-029 | TC-SAL-009 | Sales | Quotation Management | Integration | Convert quotation to order | QT-1003 | Sales order should be generated | Sales order generated correctly | Pass | - | Integration verified
EXEC-030 | TC-SAL-010 | Sales | Quotation Management | Object | Verify quotation save button | Save Quotation | Button should be available | Button available | Pass | - | Object verified
EXEC-031 | TC-SAL-011 | Sales | Sales Order Management | Functional | Create sales order | SO-1001 Qty 10 | Order should be created | Order created successfully | Pass | - | Verified
EXEC-032 | TC-SAL-012 | Sales | Sales Order Management | UI | Verify order form | Customer and product | Form should display correctly | Form displayed correctly | Pass | - | Verified
EXEC-033 | TC-SAL-013 | Sales | Sales Order Management | Regression | Verify existing sales order | SO-1002 | Order should remain accessible | Order accessible | Pass | - | Regression passed
EXEC-034 | TC-SAL-014 | Sales | Sales Order Management | Integration | Verify order updates inventory | SO-1003 Qty 5 | Inventory should reflect order | Inventory updated correctly | Pass | - | Integration verified
EXEC-035 | TC-SAL-015 | Sales | Sales Order Management | Object | Verify order submit button | Submit Order | Button should work correctly | Button worked correctly | Pass | - | Object verified
EXEC-036 | TC-SAL-016 | Sales | Invoicing | Functional | Generate invoice | INV-1001 ₹25000 | Invoice should be generated | Invoice generated successfully | Pass | - | Verified
EXEC-037 | TC-SAL-017 | Sales | Invoicing | UI | Verify invoice layout | Customer invoice | Invoice fields should display correctly | Invoice displayed correctly | Pass | - | Verified
EXEC-038 | TC-SAL-018 | Sales | Invoicing | Regression | Verify existing invoice | INV-1002 | Invoice should remain accessible | Invoice accessible | Pass | - | Regression passed
EXEC-039 | TC-SAL-019 | Sales | Invoicing | Integration | Verify invoice updates receivable | INV-1003 | Receivable should be updated | Receivable updated correctly | Pass | - | Integration verified
EXEC-040 | TC-SAL-020 | Sales | Invoicing | Object | Verify print invoice button | Print Invoice | Button should be available | Button displayed correctly | Pass | - | Object verified
EXEC-041 | TC-PRO-001 | Production | Production Planning | Functional | Create production plan | PP-1001 Qty 100 | Plan should be created | Plan created successfully | Pass | - | Verified
EXEC-042 | TC-PRO-002 | Production | Production Planning | UI | Verify planning fields | Product FG-1001 | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-043 | TC-PRO-003 | Production | Production Planning | Regression | Verify existing production plan | PP-1002 | Plan should remain accessible | Plan accessible | Pass | - | Regression passed
EXEC-044 | TC-PRO-004 | Production | Production Planning | Integration | Verify plan creates work order | PP-1003 | Work order should be generated | Work order generated correctly | Pass | - | Integration verified
EXEC-045 | TC-PRO-005 | Production | Production Planning | Object | Verify create plan button | Create Plan | Button should be available | Button displayed correctly | Pass | - | Object verified
EXEC-046 | TC-PRO-006 | Production | Work Orders | Functional | Create work order | WO-1001 | Work order should be created | Work order created successfully | Pass | - | Verified
EXEC-047 | TC-PRO-007 | Production | Work Orders | UI | Verify work order screen | WO-1002 | Screen should display correctly | Screen displayed correctly | Pass | - | Verified
EXEC-048 | TC-PRO-008 | Production | Work Orders | Regression | Verify existing work order | WO-1003 | Work order should remain available | Work order available | Pass | - | Regression passed
EXEC-049 | TC-PRO-009 | Production | Work Orders | Integration | Verify material allocation | RM-1001 Qty 20 | Material should be allocated | Material allocated correctly | Pass | - | Integration verified
EXEC-050 | TC-PRO-010 | Production | Work Orders | Object | Verify status dropdown | WO-1004 | Status control should work | Status control worked | Pass | - | Object verified
EXEC-051 | TC-PRO-011 | Production | Bill of Materials | Functional | Create BOM | BOM-1001 | BOM should be created | BOM created successfully | Pass | - | Verified
EXEC-052 | TC-PRO-012 | Production | Bill of Materials | UI | Verify BOM fields | RM-1001 Qty 5 | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-053 | TC-PRO-013 | Production | Bill of Materials | Regression | Verify existing BOM | BOM-1002 | BOM should remain accessible | BOM accessible | Pass | - | Regression passed
EXEC-054 | TC-PRO-014 | Production | Bill of Materials | Integration | Verify BOM used in production | FG-1001 | BOM should be available to production | BOM available correctly | Pass | - | Integration verified
EXEC-055 | TC-PRO-015 | Production | Bill of Materials | Object | Verify add material button | Add Material | Button should work | Button worked correctly | Pass | - | Object verified
EXEC-056 | TC-HR-001 | Human Resources | Employee Management | Functional | Create employee | EMP-1001 Employee A | Employee should be created | Employee created successfully | Pass | - | Verified
EXEC-057 | TC-HR-002 | Human Resources | Employee Management | UI | Verify employee form | Employee details | Form should display correctly | Form displayed correctly | Pass | - | Verified
EXEC-058 | TC-HR-003 | Human Resources | Employee Management | Regression | Verify existing employee | EMP-1002 | Employee should remain available | Employee available | Pass | - | Regression passed
EXEC-059 | TC-HR-004 | Human Resources | Attendance Management | Functional | Record attendance | EMP-1001 Present | Attendance should be recorded | Attendance recorded successfully | Pass | - | Verified
EXEC-060 | TC-HR-005 | Human Resources | Attendance Management | UI | Verify attendance screen | EMP-1001 | Screen should display correctly | Screen displayed correctly | Pass | - | Verified
EXEC-061 | TC-HR-006 | Human Resources | Leave Management | Functional | Submit leave request | EMP-1001 2 Days | Leave request should be submitted | Leave request submitted successfully | Pass | - | Verified
EXEC-062 | TC-HR-007 | Human Resources | Leave Management | Regression | Verify leave history | EMP-1001 | Previous leave should remain available | Leave history displayed | Pass | - | Regression passed
EXEC-063 | TC-HR-008 | Human Resources | Payroll | Functional | Process payroll | EMP-1001 ₹30000 | Payroll should be processed | Payroll processed successfully | Pass | - | Verified
EXEC-064 | TC-HR-009 | Human Resources | Payroll | Integration | Verify payroll posting | PAY-1001 | Salary should be posted to Finance | Salary posted correctly | Pass | - | Integration verified
EXEC-065 | TC-HR-010 | Human Resources | Payroll | Object | Verify payroll process button | Process Payroll | Button should be available | Button displayed correctly | Pass | - | Object verified
EXEC-066 | TC-PUR-001 | Purchase | Vendor Management | Functional | Create vendor | VEN-001 XYZ Suppliers | Vendor should be created | Vendor created successfully | Pass | - | Verified
EXEC-067 | TC-PUR-002 | Purchase | Vendor Management | UI | Verify vendor form | Vendor details | Form should display correctly | Form displayed correctly | Pass | - | Verified
EXEC-068 | TC-PUR-003 | Purchase | Vendor Management | Regression | Verify existing vendor | VEN-002 | Vendor should remain available | Vendor available | Pass | - | Regression passed
EXEC-069 | TC-PUR-004 | Purchase | Purchase Requisition | Functional | Create purchase requisition | PR-1001 Qty 20 | Requisition should be created | Requisition created successfully | Pass | - | Verified
EXEC-070 | TC-PUR-005 | Purchase | Purchase Requisition | Integration | Verify requisition creates PO | PR-1002 | Purchase order should be generated | Purchase order generated correctly | Pass | - | Integration verified
EXEC-071 | TC-PUR-006 | Purchase | Purchase Order | Functional | Create purchase order | PO-1001 Qty 50 | Purchase order should be created | Purchase order created successfully | Pass | - | Verified
EXEC-072 | TC-PUR-007 | Purchase | Purchase Order | UI | Verify purchase order fields | Vendor and product | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-073 | TC-PUR-008 | Purchase | Purchase Order | Regression | Verify existing PO | PO-1002 | PO should remain accessible | PO accessible | Pass | - | Regression passed
EXEC-074 | TC-PUR-009 | Purchase | Purchase Order | Integration | Verify PO updates inventory | PO-1003 Qty 60 | Inventory should update after receipt | Inventory updated correctly | Pass | - | Integration verified
EXEC-075 | TC-PUR-010 | Purchase | Purchase Invoice | Functional | Create purchase invoice | PINV-1001 ₹40000 | Invoice should be created | Purchase invoice created successfully | Pass | - | Verified
EXEC-076 | TC-INV-001 | Inventory | Item Management | Functional | Create inventory item | PROD-1001 Laptop | Item should be created | Item created successfully | Pass | - | Verified
EXEC-077 | TC-INV-002 | Inventory | Item Management | UI | Verify item form | Product details | Form should display correctly | Form displayed correctly | Pass | - | Verified
EXEC-078 | TC-INV-003 | Inventory | Item Management | Regression | Verify existing item | PROD-1002 | Item should remain available | Item available | Pass | - | Regression passed
EXEC-079 | TC-INV-004 | Inventory | Stock Management | Functional | Update stock quantity | PROD-1001 Qty 50 | Stock should be updated | Stock updated successfully | Pass | - | Verified
EXEC-080 | TC-INV-005 | Inventory | Stock Management | Integration | Verify sales order reduces stock | SO-1004 Qty 10 | Stock should reduce by order quantity | Stock reduced correctly | Pass | - | Integration verified
EXEC-081 | TC-INV-006 | Inventory | Warehouse Management | Functional | Assign item to warehouse | PROD-1001 WH-001 | Item should be assigned | Item assigned successfully | Pass | - | Verified
EXEC-082 | TC-INV-007 | Inventory | Warehouse Management | UI | Verify warehouse selection | WH-001 | Warehouse options should display | Warehouse options displayed | Pass | - | Verified
EXEC-083 | TC-INV-008 | Inventory | Stock Movement | Functional | Transfer stock | PROD-1001 Qty 10 | Stock should transfer successfully | Stock transferred successfully | Pass | - | Verified
EXEC-084 | TC-INV-009 | Inventory | Stock Movement | Integration | Verify warehouse stock update | WH-001 to WH-002 | Source and target stock should update | Stock updated correctly | Pass | - | Integration verified
EXEC-085 | TC-INV-010 | Inventory | Stock Management | Object | Verify stock update button | Update Stock | Button should be available | Button displayed correctly | Pass | - | Object verified
EXEC-086 | TC-LOG-001 | Logistics | Shipment Management | Functional | Create shipment | SHP-1001 | Shipment should be created | Shipment created successfully | Pass | - | Verified
EXEC-087 | TC-LOG-002 | Logistics | Shipment Management | UI | Verify shipment fields | SO-1001 | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-088 | TC-LOG-003 | Logistics | Shipment Management | Regression | Verify existing shipment | SHP-1002 | Shipment should remain accessible | Shipment accessible | Pass | - | Regression passed
EXEC-089 | TC-LOG-004 | Logistics | Delivery Management | Functional | Create delivery | DEL-1001 Qty 10 | Delivery should be created | Delivery created successfully | Pass | - | Verified
EXEC-090 | TC-LOG-005 | Logistics | Delivery Management | Integration | Verify delivery updates sales order | SO-1001 | Order status should become Delivered | Order status updated correctly | Pass | - | Integration verified
EXEC-091 | TC-SRV-001 | Service | Service Request | Functional | Create service request | SR-1001 CUST-001 | Service request should be created | Service request created successfully | Pass | - | Verified
EXEC-092 | TC-SRV-002 | Service | Service Request | UI | Verify service request screen | Customer details | Screen should display correctly | Screen displayed correctly | Pass | - | Verified
EXEC-093 | TC-SRV-003 | Service | Service Request | Regression | Verify existing service request | SR-1002 | Request should remain accessible | Request accessible | Pass | - | Regression passed
EXEC-094 | TC-SRV-004 | Service | Ticket Management | Functional | Create service ticket | TKT-1001 Priority High | Ticket should be created | Ticket created successfully | Pass | - | Verified
EXEC-095 | TC-SRV-005 | Service | Ticket Management | UI | Verify ticket fields | TKT-1001 | Fields should display correctly | Fields displayed correctly | Pass | - | Verified
EXEC-096 | TC-SRV-006 | Service | Service Assignment | Functional | Assign technician | TKT-1001 TECH-001 | Ticket should be assigned | Ticket assigned successfully | Pass | - | Verified
EXEC-097 | TC-SRV-007 | Service | Service Assignment | Integration | Verify spare part usage updates inventory | SR-1001 SP-1001 Qty 2 | Inventory should reduce spare part stock | Inventory updated correctly | Pass | - | Integration verified
EXEC-098 | TC-SRV-008 | Service | Service Status Tracking | Functional | Update service status | TKT-1001 Resolved | Status should be updated | Status updated successfully | Pass | - | Verified
EXEC-099 | TC-SRV-009 | Service | Service Status Tracking | Regression | Verify existing resolved ticket | TKT-1002 | Ticket status should remain available | Ticket status displayed correctly | Pass | - | Regression passed
EXEC-100 | TC-SRV-010 | Service | Service Status Tracking | Object | Verify status dropdown | Resolved | Status dropdown should be available | Dropdown displayed correctly | Pass | - | Object verified